|  |
| --- |
| **Progress Report** |
| **WO 009 Highway Incident Detection Timeline** |
| **Contract** | **Project** | **Billed Month** | **Vendor Name** | **Date** |
| **4400011166** | **TEM WO 009** | **October 2016** | **Temple University** | **10/31/2016** |
| **Federal ID No.** | **Vendor SAP No.** | **Project Amount** | **Billed to Date** | **Percentage Billed** |
| **23-1365971** | **117671** | **$126,000.00** | **$0.00** | **0%** |
|  |
| **Task** | **Deliverable** | **Due** | **Completed** |
| **1.1** | A report summarizing the counties contacted and the datasets acquired. | **02/17/2017** |  |
| **1.2** | An electronic copy of the raw data acquired from each source. | **02/17/2017** |  |
| **2.1** | A report summarizing the efforts involved in data integration and pre-processing. | **04/17/2017** |  |
| **2.2** | An electronic copy of the normalized data. | **04/17/2017** |  |
| **3.1** | A report summarizing analysis of the 911 call data and PennDOT highway road closure data, including estimates of PennDOT notification latency for highway incidents across the state of Pennsylvania, a description of the software and methodologies used to arrive at the estimates of latency, statistical significance and confidence measures, and a comparison of the accuracies of the various prediction models: | **06/17/2017** |  |
| **4.1** | A report of the actions performed to curate the data and direct electronic access to the data archive via a URL or project website. | **07/17/2017** |  |
| **4.2** | An electronic archival copy of the data as it exists at the end of the project. | **07/17/2017** |  |
| **5.1** | A Draft Final Report | **08/17/2017** |  |
| **6.1** | A Final Report | **10/17/2017** |  |
|  |
|  |
| **Task** | **Accomplishments This Month** | **Activities Planned For Next Month** |
| **1.1** | **1] Initiated project with kick-off meeting.****2] Assigned graduate student researcher to project and provided info to Michael Bindie.****3] Initiated contact with county 911 call centers to request data.****4] Started acquiring data from a subset of county 911 call centers.** | **1] Continue to contact county 911 call centers and acquire pertinent data.****2] Initiate efforts to acquire pertinent data from PennDOT sources, including** **PennDOT Highway Road Closure data.** |
| **1.2** | **1] Initiated efforts to develop dataset repository.** | **1] Continue adding data to the repository.** |
| **2.1** | **1] Initiated discussion regarding efforts involved in data integration and pre-processing based on an initial examination of a limited subset of 911 call center data.** | **1] Continue examining data to evaluate further efforts to normalize data.****2] Initiate data integration and pre-processing for acquired data.** |
| **2.2** |  |  |
| **3.1** |  |  |
| **4.1** |  |  |
| **4.2** |  |  |
| **5.1** |  |  |
| **6.1** |  |  |
|  |
|  |
| **Principal Investigator Comments** |
| 1] **The next conference call will be on November 23, 2017 at 11am.** |
| **I certify that the above is correct and just.** | ***Signature:* Joseph Thomas Coe, Ph.D.** | **11/11/2017** | **215-204-6100** |
|
| **(PRINTED NAME)** | **Date** | **Telephone No.** |