|  |
| --- |
| **Progress Report** |
| **WO 009 Highway Incident Detection Timeline** |
| **Contract** | **Project** | **Billed Month** | **Vendor Name** | **Date** |
| **4400011166** | **TEM WO 009** | **August 2017** | **Temple University** | **09/13/2017** |
| **Federal ID No.** | **Vendor SAP No.** | **Project Amount** | **Billed to Date** | **Percentage Billed** |
| **23-1365971** | **117671** | **$126,000.00** | **$22,050.00** | **17.5%** |
|  |
| **Task** | **Deliverable** | **Due** | **Completed** |
| **1.1** | A report summarizing the counties contacted and the datasets acquired. | **02/17/2017** | **02/17/2017** |
| **1.2** | An electronic copy of the raw data acquired from each source. | **02/17/2017** | **02/17/2017** |
| **2.1** | A report summarizing the efforts involved in data integration and pre-processing. | **04/17/2017** | **04/17/2017** |
| **2.2** | An electronic copy of the normalized data. | **04/17/2017** | **04/17/2017** |
| **3.1** | A report summarizing analysis of the 911 call data and PennDOT highway road closure data, including estimates of PennDOT notification latency for highway incidents across the state of Pennsylvania, a description of the software and methodologies used to arrive at the estimates of latency, statistical significance and confidence measures, and a comparison of the accuracies of the various prediction models: | **07/14/2017** | **07/14/2017** |
| **4.1** | A report of the actions performed to curate the data and direct electronic access to the data archive via a URL or project website. | **07/17/2017** | **07/17/2017** |
| **4.2** | An electronic archival copy of the data as it exists at the end of the project. | **07/17/2017** | **07/17/2017** |
| **5.1** | A Draft Final Report | **08/21/2017** | **08/21/2017** |
| **6.1** | A Final Report | **10/17/2017** |  |
|  |
|  |
| **Task** | **Accomplishments This Month** | **Activities Planned For Next Month** |
| **1.1** |  |  |
| **1.2** |  | **1] Finalize efforts to acquire data from any remaining counties.****2] Continue contributing any additional data to the project website repository.** |
| **2.1** |  |  |
| **2.2** |  | **1] Normalize and pre-process any data obtained from final efforts to contact remaining counties.** |
| **3.1** | **1] Completed pairing efforts with GUI for Franklin and Centre county and incorporated into Task 5.1 deliverable report.****2] Performed statistical analyses on pairings between PennDOT RCRS and 911 data for Franklin and Centre counties.** | **1] Submit revised Task 3.1 deliverable report based on feedback from PennDOT** |
| **4.1** | **1] Submitted revised Task 4.1 deliverable report based on feedback from PennDOT.** |  |
| **4.2** | **1] Revised website prior to submission of Task 5.1 deliverable report on 08/21/2017.** | **1] Perform additional review of website to ensure data curation efforts are up to date prior to submission of revised draft final report.** |
| **5.1** | **1] Compile previous deliverable reports into comprehensive review of project efforts for draft final report.****2] Incorporate results from any additional pairing and statistical analysis efforts.** | **1] Submit revised Task 5.1 deliverable report based on feedback from PennDOT** |
| **6.1** |  | **1] Initiate Final Report based on feedback from Task 5.1 draft final report and feedback from PennDOT** |
|  |
|  |
| **Principal Investigator Comments** |
| 1] **The next conference call is scheduled for September 21, 2017 at 10:00 a.m.** |
| **I certify that the above is correct and just.** | ***Signature:* Joseph Thomas Coe, Ph.D.** | **09/13/2017** | **215-204-6100** |
|
| **(PRINTED NAME)** | **Date** | **Telephone No.** |